SuperviseAI

Feature-by-Feature Sprint Plan

Feb 25 (now)  →  Feb 28, 10:00 AM  ·  ~72 hours  ·  npm workspaces monorepo

| Phase | When | Hours | Goal |
| --- | --- | --- | --- |
| Phase 0 | Feb 25 · Today | 0 – 4h | Monorepo setup, Supabase, auth, API skeleton, env vars sorted |
| Phase 1 | Feb 25 – 26 | 4 – 20h | Core features: ThesisTrack + Professor Dashboard + Student Submit |
| Phase 2 | Feb 26 – 27 | 20 – 38h | AI Coach (Argument Defender + Mock Viva), Plagiarism, Citations |
| Phase 3 | Feb 27 | 38 – 50h | Milestone Tracker, Analytics Dashboard, StudentView polish |
| Phase 4 | Feb 27 – 28 | 50 – 65h | UI polish, seed data, bug fixes, demo prep, video, slides |

Priority rule: complete each feature fully before starting the next. If time runs short, everything already built is a working, demoable product. Nothing is left half-finished.

# Monorepo Structure — npm Workspaces

The monorepo is the first thing to set up — everything else depends on it. Use npm workspaces with three packages: web (React frontend), api (Node/Express backend), and shared (types and utilities used by both).

| supervise-ai/ | Root — package.json with workspaces config |
| --- | --- |
| packages/web/ | React.js (Vite) frontend application |
| packages/api/ | Node.js + Express backend server |
| packages/shared/ | Shared TypeScript types, constants, utils |
| .env.root | Shared env vars (Supabase URL, keys, Azure, Copyleaks) |
| package.json | Workspaces: ['packages/*'], shared dev scripts |
| turbo.json (optional) | Add Turborepo later only if build speed becomes an issue |

Root package.json workspaces config

{ "name": "supervise-ai", "workspaces": ["packages/*"], "scripts": { "dev:web": "npm run dev -w packages/web", "dev:api": "npm run dev -w packages/api", "dev": "npm run dev:api & npm run dev:web" } }

Shared package — types used by both web and api

The shared package should define TypeScript interfaces for the core data models: User, Submission, ThesisAnalysis, PlagiarismReport, CitationReport, CoachingSession, Milestone. Both packages import from @supervise-ai/shared — this prevents the frontend and backend from drifting out of sync on data shapes.

| Phase 0 | Foundation & Setup | Feb 25 · Hours 0 – 4 |
| --- | --- | --- |

Do this before writing a single feature. Every hour spent here saves three hours of debugging later. All four team members work in parallel on their own setup tasks.

| 0.1 Monorepo Init + GitHub · 1 hour · BLOCKER |  |
| --- | --- |
| Owner Team Lead | Create the repo, set up npm workspaces, push to GitHub, add all team members. |
| → | mkdir supervise-ai && cd supervise-ai && git init |
| → | Create packages/web (Vite React), packages/api (Express), packages/shared |
| → | Set up root package.json with workspaces and dev scripts |
| → | Push to GitHub, create main and dev branches, protect main |
| → | Share repo access with all team members |

| 0.2 Supabase Project Setup · 1 hour · BLOCKER |  |
| --- | --- |
| Owner Senior Backend Dev | Create Supabase project, run schema migrations, configure storage buckets and auth. |
| → | Create new Supabase project — note URL and anon/service keys |
| → | Run SQL to create all tables: users, cohorts, enrollments, milestones, submissions, thesis_analysis, plagiarism_reports, citation_reports, coaching_sessions |
| → | Enable Row Level Security on all tables |
| → | Create storage bucket: thesis-drafts (private) |
| → | Enable email auth, set professor and student roles in user metadata |
| → | Add all keys to .env.root |

| 0.3 API Skeleton + Auth Middleware · 1 hour · BLOCKER |  |
| --- | --- |
| Owner Senior Backend Dev | Scaffold Express app with all route files stubbed, Supabase client connected, JWT middleware working. |
| → | Install: express, @supabase/supabase-js, dotenv, multer, cors, pdf-parse, mammoth |
| → | Create route files: /auth, /submissions, /analysis, /coaching, /milestones, /dashboard — all returning 200 stubs |
| → | Add JWT auth middleware that reads Supabase session and attaches user to req |
| → | Test: POST /auth/login returns token, protected route rejects without token |

| 0.4 React App Scaffold + Auth UI · 1.5 hours · BLOCKER |  |
| --- | --- |
| Owner Junior Full-Stack Dev | Vite React app running, Supabase auth connected, login/register page working, role-based routing in place. |
| → | Install: react, react-router-dom, @supabase/supabase-js, axios, tailwindcss |
| → | Create Login and Register pages — email + password + role selector (Professor / Student) |
| → | On login, store Supabase session token, redirect based on role |
| → | Create placeholder pages: /professor/dashboard, /student/home — protected routes |
| → | Test: Professor logs in → sees professor dashboard stub. Student logs in → sees student dashboard stub. |

| Phase 1 | Core — ThesisTrack + Dashboards | Feb 25–26 · Hours 4 – 20 |
| --- | --- | --- |

This is the heart of the product. Get this working end-to-end first. A student can upload a draft, the AI analyses it, and the professor sees the result. Everything else builds on top of this loop.

| 1.1 File Upload + Text Extraction · 2 hours · CRITICAL |  |
| --- | --- |
| Owner Senior Backend Dev | Student uploads a PDF or DOCX. Backend saves it to Supabase Storage and extracts raw text. This is the foundation all analysis depends on. |
| → | POST /submissions endpoint: accept multipart file upload via multer |
| → | Save file to Supabase Storage under path: {userId}/{submissionId}/{filename} |
| → | Detect file type — run pdf-parse for PDF, mammoth.js for DOCX |
| → | Save extracted text to submissions table (text column) |
| → | Return submissionId to client — client uses this to poll for analysis results |
| → | Test with a real PDF and a real DOCX — confirm clean text extraction |

| 1.2 ThesisTrack — AI Analysis Pipeline · 4 hours · CRITICAL |  |
| --- | --- |
| Owner Data Science Dev | The core AI feature. Once text is extracted, fire the analysis pipeline and store results. This is what makes SuperviseAI intelligent. |
| → | After text extraction, fetch previous submission text for same student (if exists) from Supabase |
| → | Run diff-match-patch on old vs new text — extract structural diff summary |
| → | Build GPT-4o prompt: pass full text + diff summary + milestone stage context |
| → | Prompt asks for: direction_aligned (bool), gap_report (JSON array of weak/missing sections), next_steps (JSON array of prioritised actions), progress_score (0-100) |
| → | Parse GPT-4o response, save to thesis_analysis table linked to submissionId |
| → | Update submission status from 'processing' to 'complete' |
| → | Test: upload two drafts for same student, confirm diff and analysis both return correctly |

| 1.3 Professor Dashboard · 3 hours · CRITICAL |  |
| --- | --- |
| Owner Junior Full-Stack Dev | The professor's main view. All supervised students listed with their latest submission status, progress score, and AI summary note. |
| → | GET /dashboard/professor/:id — returns all students with latest submission + analysis summary |
| → | Professor dashboard page: table/card list of students |
| → | Each student row: name, last submission date, progress score (colour-coded), one-line AI status note |
| → | Click on student → navigates to student detail page (Feature 1.4) |
| → | Empty state: 'No students yet — share your cohort code to get started' |
| → | Loading skeleton while data fetches |

| 1.4 Student Detail Page (Professor View) · 2 hours · CRITICAL |  |
| --- | --- |
| Owner Junior Full-Stack Dev | Professor clicks a student and sees their full analysis: diff viewer, gap report, next steps, progress score. |
| → | GET /analysis/thesis/:submissionId — returns full ThesisTrack result |
| → | Student detail page: progress score badge, direction aligned indicator |
| → | Diff viewer: side-by-side or inline view of what changed between versions |
| → | Gap report: list of missing/weak sections with severity indicator |
| → | Next steps: numbered list of AI-recommended actions |
| → | Submission history: dropdown to view analysis from any past submission |

| 1.5 Student Submit Page · 2 hours · CRITICAL |  |
| --- | --- |
| Owner Junior Full-Stack Dev | Student uploads a new draft, sees upload progress, then sees their own analysis result when ready. |
| → | Student home page: current progress score, last submission date, next milestone |
| → | Upload button → file picker (PDF/DOCX only, max 20MB) |
| → | Show upload progress bar, then 'Analysis in progress...' spinner |
| → | Poll GET /submissions/:id every 4 seconds until status = complete |
| → | When complete: show their own ThesisTrack result — progress score, gaps, next steps |
| → | Show previous vs current diff so student sees their own improvement |

| Phase 2 | AI Coach + Plagiarism + Citations | Feb 26–27 · Hours 20 – 38 |
| --- | --- | --- |

This phase is what wins the hackathon challenge prize. The AI Coach directly answers the brief. Plagiarism and Citation Validator add serious depth and show technical maturity.

| 2.1 AI Coach — Argument Defender · 3 hours · HIGH |  |
| --- | --- |
| Owner Data Science Dev | Student selects a chapter. AI reads it and challenges the student's core arguments. Student responds, AI pushes back. Session ends with a structured feedback report. |
| → | POST /coaching/start — takes submissionId + mode='argument_defender' |
| → | Backend fetches thesis text for that submission from Supabase |
| → | GPT-4o prompt: extract 3-5 core claims from the chapter, return as JSON array |
| → | POST /coaching/message — takes sessionId + student message, returns AI response |
| → | AI maintains session context — each response references the student's previous answer |
| → | After 3 exchanges per claim, AI generates feedback: argument strength score, evidence quality, logical consistency |
| → | POST /coaching/end — saves full session + feedback report to coaching_sessions table |
| → | Professor can see session summary on student detail page |

| 2.2 AI Coach UI — Chat Interface · 2 hours · HIGH |  |
| --- | --- |
| Owner Junior Full-Stack Dev | Clean chat interface for the Argument Defender coaching session. Student sees AI challenges, types responses, sees live feedback. |
| → | Coaching page: chapter selector dropdown (populated from submission sections) |
| → | Chat window: AI message bubbles (left), student message bubbles (right) |
| → | Text input with send button — disabled while AI is responding |
| → | Typing indicator while waiting for AI response |
| → | Progress indicator: 'Claim 2 of 5 — Defending your methodology' |
| → | End session button → shows final feedback report with scores |
| → | Feedback report: three scored criteria with short explanation each |

| 2.3 AI Coach — Mock Viva (Voice) · 4 hours · HIGH |  |
| --- | --- |
| Owner Data Science Dev + Senior Backend Dev | The showstopper demo feature. AI reads the full thesis and conducts a spoken viva examination. Student speaks answers, AI responds aloud. Azure powers the voice layer. |
| → | POST /coaching/start with mode='mock_viva' — AI generates 8-10 viva questions from full thesis |
| → | Backend: Azure Speech-to-Text SDK — stream student microphone input, return transcript |
| → | Backend: Azure Text-to-Speech — convert AI examiner question to audio, stream to client |
| → | Backend: Azure Cognitive Services — sentiment/confidence analysis on student transcript |
| → | AI adapts next question based on confidence score — easier follow-up if hesitant, harder if confident |
| → | Store full session transcript + confidence scores + viva readiness score in coaching_sessions |
| → | End of session: viva readiness report — overall score, strongest section, weakest section, recommended prep areas |

| 2.4 Mock Viva UI — Voice Interface · 2 hours · HIGH |  |
| --- | --- |
| Owner Junior Full-Stack Dev | Voice-based UI for the Mock Viva. Student sees the AI examiner speaking, their transcript appearing, and live confidence feedback. |
| → | Mock Viva page: full-screen focused mode — no navigation distractions |
| → | AI examiner panel: animated speaking indicator when AI is talking, question text displayed |
| → | Student panel: microphone button (hold to speak or toggle), live transcript appearing as they speak |
| → | Confidence indicator: subtle colour signal showing detected confidence level |
| → | Session progress: 'Question 3 of 8' |
| → | End viva button → shows readiness report with scores and preparation recommendations |
| → | Use Web Speech API as fallback if Azure Speech has latency issues during demo |

| 2.5 Plagiarism Check — Copyleaks Integration · 2 hours · HIGH |  |
| --- | --- |
| Owner Senior Backend Dev | Automatic plagiarism check on every submission. Runs alongside ThesisTrack. Checks internet + internal DB simultaneously. |
| → | Install Copyleaks Node.js SDK: npm install copyleaks-sdk -w packages/api |
| → | After text extraction, fire Copyleaks scan as a parallel job (do not block ThesisTrack) |
| → | Copyleaks is async — store scanId, set up webhook endpoint POST /webhooks/copyleaks |
| → | Webhook receives result → save originality_score + flagged_passages JSON to plagiarism_reports table |
| → | If originality drops >10% from previous submission, set alert flag in DB |
| → | Student and professor both see originality score on the submission result page |
| → | Test: submit a paragraph copied from Wikipedia — confirm it is flagged |

| 2.6 Citation & Reference Validator · 3 hours · MEDIUM |  |
| --- | --- |
| Owner Data Science Dev | Three-layer citation check on every submission. Cross-reference check (Node.js), format validation (GPT-4o), source existence (Semantic Scholar). No new paid APIs. |
| → | Layer 1 — Regex: extract all in-text citations and bibliography entries from parsed text |
| → | Compare both lists — flag citations with no bibliography match and orphaned bibliography entries |
| → | Layer 2 — GPT-4o: detect citation style (APA/MLA/IEEE/Harvard), validate each bibliography entry format, return flagged entries with error + suggested fix |
| → | Layer 3 — Semantic Scholar: for each bibliography entry, extract title/DOI, query https://api.semanticscholar.org/graph/v1/paper/search, flag entries with no match as 'Unverifiable' |
| → | Merge all three layers into citation_reports table |
| → | Display on submission result page: summary card + expandable full breakdown |
| → | Test: submit a thesis with one fake AI-generated reference — confirm Layer 3 flags it |

| Phase 3 | Milestones + Analytics + Polish | Feb 27 · Hours 38 – 50 |
| --- | --- | --- |

Phase 3 adds the structural and analytical layer on top of everything already built. These features are important but the product is already demoable without them. Build them fully if time allows.

| 3.1 Milestone & Deadline Tracker · 3 hours · MEDIUM |  |
| --- | --- |
| Owner Junior Full-Stack Dev + Senior Backend Dev | Professor sets thesis milestones with deadlines. Students submit against milestones. ThesisTrack scoring becomes contextual — evaluated against the expected stage. |
| → | POST /milestones — professor creates milestone: title, due_date, stage enum (proposal/lit_review/methodology/full_draft/final) |
| → | GET /milestones/cohort/:id — returns all milestones with student completion status |
| → | Student submit page: milestone selector dropdown before upload |
| → | Pass milestone stage to ThesisTrack prompt — AI evaluates draft against what is expected at this stage specifically |
| → | Professor dashboard: milestone column showing which milestone each student is on |
| → | Student home: visual timeline of milestones — completed (green), current (blue), upcoming (grey) |
| → | Overdue milestone: red indicator on both professor and student views |

| 3.2 Professor Analytics Dashboard · 2.5 hours · MEDIUM |  |
| --- | --- |
| Owner Data Science Dev | Aggregated insights across all supervised students. At-risk alerts, cohort weak spots, submission velocity trends. |
| → | GET /dashboard/analytics/:professorId — aggregates across all students and submissions |
| → | At-risk students: those with no submission in 14+ days OR progress_score declining over last 2 submissions |
| → | Cohort weak spots: count which thesis sections are most frequently flagged in gap_report across all students |
| → | Submission velocity: average submissions per student per week |
| → | Analytics page: at-risk student list with alert badges, cohort weak spots bar chart, individual progress sparklines |
| → | Keep charts simple — use a lightweight library like Chart.js or Recharts |

| 3.3 Socratic Writing Coach · 2 hours · MEDIUM |  |
| --- | --- |
| Owner Data Science Dev | Third coaching mode. Student describes what they are stuck on. AI asks guiding questions instead of giving answers. Session produces a structured outline. |
| → | POST /coaching/start with mode='socratic' — takes student's stuck description as input |
| → | GPT-4o prompt: Socratic guide role, do not provide answers, only ask questions that guide the student toward their own answer |
| → | AI adapts question complexity based on quality of student response |
| → | After 5-7 exchanges, AI generates a structured outline the student can write from immediately |
| → | Reuse the same chat UI from Feature 2.2 — just different mode and system prompt |
| → | Add Socratic mode to the coaching selection screen |

| Phase 4 | Polish + Demo Prep + Submission | Feb 27–28 · Hours 50 – 72 |
| --- | --- | --- |

The last stretch. No new features. Focus is entirely on making what exists look and feel finished, seeding realistic demo data, and preparing the submission deliverables.

| 4.1 Seed Demo Data · 1.5 hours · CRITICAL |  |
| --- | --- |
| Owner Team Lead | Create realistic demo accounts and data so the demo flows smoothly without live typing or waiting. |
| → | Create 2 professor accounts and 4 student accounts in Supabase |
| → | Upload 2 real thesis draft versions for 2 students (find open-access university theses) |
| → | Ensure ThesisTrack analysis, plagiarism report, and citation report all exist for demo submissions |
| → | One student should have an at-risk flag (no submission in 14 days) for the analytics demo |
| → | One submission should have a flagged citation for the Citation Validator demo |
| → | Pre-run a coaching session transcript for the Argument Defender demo |

| 4.2 UI Polish Pass · 3 hours · HIGH |  |
| --- | --- |
| Owner Junior Full-Stack Dev | Make the app look finished. Consistent colours, loading states, error handling, empty states, responsive layout. |
| → | Add loading skeletons on all data-fetching pages |
| → | Add error boundaries — never show a white screen crash during the demo |
| → | Consistent colour usage — blue for professor UI, green for student UI |
| → | Add SuperviseAI logo/wordmark to navbar |
| → | Make sure all tables and cards look good on a laptop screen at 1280px width |
| → | Add subtle transitions on page navigation |
| → | Remove all console.log statements and TODO comments |

| 4.3 Demo Video (2 minutes) · 2 hours · CRITICAL |  |
| --- | --- |
| Owner Team Lead | Record the required 2-minute demo video. Plan the exact script before recording — every second counts. |
| → | Script: 0:00–0:20 — problem statement (professor overwhelmed, student unprepared for viva) |
| → | Script: 0:20–0:45 — student uploads draft, ThesisTrack analysis appears |
| → | Script: 0:45–1:05 — plagiarism score + citation report shown |
| → | Script: 1:05–1:35 — Mock Viva demo — student speaks, AI examiner responds aloud (most impressive moment) |
| → | Script: 1:35–1:50 — professor dashboard — all students, at-risk alert, analytics |
| → | Script: 1:50–2:00 — product name, tagline, team |
| → | Record with OBS or Loom, do at least 3 takes, use the cleanest one |

| 4.4 Presentation Slides (min 5 slides) · 1.5 hours · CRITICAL |  |
| --- | --- |
| Owner Team Lead | The pitch deck. Clear, visual, confident. Judges score on presentation quality for the grand prize. |
| → | Slide 1 — Problem: one powerful statistic about thesis supervision burden |
| → | Slide 2 — Solution: SuperviseAI in one sentence + the three user benefits |
| → | Slide 3 — Product: screenshot of professor dashboard + student Mock Viva UI |
| → | Slide 4 — Technology: Azure services highlighted, architecture in one clean diagram |
| → | Slide 5 — Impact: who benefits, how many students/professors, future potential |
| → | Optional Slide 6 — Team: names and roles |
| → | Keep slides minimal — big visuals, short text, let the demo video do the talking |

| 4.5 Final Submission Checklist · 30 min · CRITICAL |  |
| --- | --- |
| Owner Team Lead | Verify all required deliverables are ready and submitted before 10am on the 28th. |
| → | GitHub repo: public, README with setup instructions, clean commit history |
| → | YouTube video: unlisted or public, exactly under 2 minutes, clear audio |
| → | Project description: problem, solution, value — 200 to 300 words |
| → | Presentation slides: minimum 5 slides, exported as PDF |
| → | Test the live demo URL one final time before submission |
| → | Submit all links through the hackathon portal before 10:00 AM on February 28th |

# Risk Register

Know the risks before you hit them. Each one has a mitigation so the team never gets stuck for more than 30 minutes.

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Copyleaks async webhook takes too long during demo | Medium | Pre-run plagiarism scan on demo data before presenting. Show cached result — no live wait needed. |
| Azure Speech latency in Mock Viva | Medium | Implement Web Speech API (browser native) as immediate fallback. Switch seamlessly if Azure lags. |
| GPT-4o rate limits hit during demo | Low | Cache all analysis results for demo submissions. Never call GPT-4o live during the presentation. |
| PDF text extraction fails on complex formatting | Medium | Test with actual thesis PDFs early in Phase 1. Have a plain-text fallback input option on the upload page. |
| Semantic Scholar API rate limited (100 req/5 min) | Low | Batch citation queries. Cache results. For demo, pre-run citation validation on demo thesis. |
| Team gets blocked on a single feature | Medium | Each feature is independent after Phase 1. If someone is stuck >45 min, skip to next feature and return later. |
| Run out of time before Phase 3 | Medium | Phase 1 + Phase 2 is already a complete, impressive product. Phase 3 is enhancement, not survival. |

SuperviseAI Sprint Plan  ·  GDE MIT Hackathon 2026  ·  Feb 25–28, Budapest